## Slide 1: Project Status Report: Scrumdog Millionaire
Executive Summary | The objectives of the Blue Ridge website project include increasing public awareness and engagement, improving the process of animal adoption, and streamlining the shelter's operations. The scope of the project includes the design, development, and implementation of the website.
Recent Accomplishments
Created a new version of the PMP Recently presented our first demo and received feedback Implemented feedback into Demo 2 Revised portions of the RTM
Next Steps
Continue making additions to live site. Continue testing functionality of the website and bug fixing. Prepare to receive feedback on website from stakeholders during Demo 2. Update documentation accordingly as website modules are finished, and update project management plan for future milestones before final demo. Complete team feedback forms. Prepare budgeting information in the event that our project is chosen for implementation.
Milestones |  |  | 
Milestone | Baseline | Expected | RAG
Project Management Plan and other |  | 2/6/2023 | C
Creation of website |  | 2/14/2023 | G
Finalization of Website |  | 4/14/2023 | G
Risks, Issues, and Dependencies
Risk: Unable to add all wanted features Risk: Bugs showing up during the presentation of Demo I Risk: Some computers are not able to see some of the images/videos we insert on our website, while others are, this could be due to the differing resolutions Issue: Funds needed to purchase domain and various other internet necessities Issue: Large amounts of differing feedback from Demo I
Status Key: | Green: On Target | Amber: Risks to Timeline, Scope, or Budget | Red: Requires Corrective Action | Complete: Work Complete
Status Date | 3/30/2023
Execution Owner | Scrumdog Millionaire
Project ID | Blue Ridge Animal Shelter Website
RAG Status | Green
Notes: Need a high-level dashboard for operational leaders. Must tell the whole story (single source of truth for staffing, outreach, engagement, etc.).
Focus on CM and DM first. We don’t have good contact information for members. Bi-weekly update meeting.